## Sheet1
Defect ID | Summary | Component | Severity | Priority | Steps to Reproduce | Expected Result | Actual Result | Status
DEF-001 | API accepts past departure dates during booking request | Booking API | Critical | High | 1. Intercept /api/v1/bookings request. 2. Set departureDate to "2020-01-01". 3. Submit payload. | API returns HTTP 400 Bad Request with date validation error. | API returns HTTP 201 Created and confirms booking for past date. | Open
DEF-002 | Duplicate bookings created on rapid checkout clicks | Checkout UI | High | High | 1. Add ticket to cart. 2. Proceed to payment. 3. Rapidly double-click "Confirm and Pay" button. | Button disables on first click; single booking reference generated. | Two separate booking references generated and charged to account. | Triaged
DEF-003 | SQL exception trace displayed on special character entry in surname | User Profile | High | Medium | 1. Navigate to Edit Profile. 2. Input ' OR '1'='1 in Surname field. 3. Click Save. | Field displays standard validation error: "Invalid characters in surname." | Raw SQL syntax exception stack trace rendered on UI screen. | In Progress
DEF-004 | 16-25 Railcard discount calculated as 50% instead of 33% | Pricing Engine | High | High | 1. Select Off-Peak journey (£100 standard). 2. Apply active 16-25 Railcard. 3. View basket total. | Final price is £67.00 (33% discount applied). | Final price displays as £50.00 (50% discount incorrectly applied). | Ready for Retest
DEF-005 | Selected seat reservation lost after browser refresh on payment page | Seat Selection | Medium | Medium | 1. Select seat 14A. 2. Proceed to Payment. 3. Refresh browser (F5). | Seat 14A remains locked for current user session. | Seat lock drops immediately and seat status reverts to Available. | Closed
DEF-006 | Ticket quantity input accepts negative integers (-5) | Cart Subsystem | Medium | High | 1. Navigate to ticket selection. 2. Manually input "-5" into Quantity field. 3. Click Add to Cart. | Validation error displays: "Quantity must be a positive integer." | Cart total subtracts fare value, resulting in negative order balance. | Open
DEF-007 | Session token remains valid after user explicitly logs out | Authentication | Critical | High | 1. Log in. 2. Copy Bearer token from headers. 3. Click Logout. 4. Send API call with copied token. | API returns HTTP 410 Unauthorized for invalidated session token. | API returns HTTP 200 OK and executes profile action using invalidated token. | Triaged
DEF-008 | PDF ticket download generates corrupted 0KB file on Firefox | Order History | Medium | Low | 1. Open Firefox browser. 2. Go to My Bookings. 3. Click "Download E-Ticket PDF". | PDF opens correctly with full trip barcode details. | File downloads as 0KB "ticket_JG.pdf" and fails to open in viewer. | Open
DEF-009 | Password reset endpoint allows unlimited retry attempts without lockout | Security Auth | High | High | 1. Target POST /api/v1/auth/reset-password. 2. Fire 100 rapid requests with random PINs. | Account locks temporarily after 5 failed attempts (Rate Limiting HTTP 429). | System processes all 100 requests without rate limiting or IP lockout. | In Progress
DEF-010 | Departure and Arrival stations can be selected as the exact same location | Search Module | Low | Low | 1. Select Departure: "London King's Cross". 2. Select Arrival: "London King's Cross". 3. Click Search. | Validation message triggers: "Departure and Arrival stations must differ." | System processes query and displays zero-minute duration route for full price. | Open
DEF-011 | Mobile viewport truncates train schedule arrival times below 375px width | UI Layout | Low | Low | 1. Open app on screen width < 375px. 2. Perform journey search. 3. View results list. | Arrival timestamps display fully aligned with station names. | Arrival time text wraps off-screen behind edge border. | Ready for Retest
DEF-012 | Expired Railcard allows discount selection without error prompt | Validation UI | High | High | 1. Attach Railcard with expiry date "2023-01-01". 2. Attempt journey checkout with discount option checked. | System rejects discount: "Railcard expired. Please update details." | Discount applies to subtotal without raising expired status warning. | Triaged
DEF-013 | DB payment status remains "Pending" when gateway times out | Payment Service | High | High | 1. Mock 30s timeout response from payment provider. 2. Submit booking payment request. | Booking state transitions to "Failed" after 15-second gateway timeout. | Database row stays locked in "Pending" status indefinitely. | In Progress
DEF-014 | Special Characters in Station Search trigger unhandled 500 error | Search Engine | Medium | Medium | 1. Input "<script>alert(1)</script>" into station search input box. 2. Click Search. | Input sanitized cleanly; returns "No matching station found." | Browser throws HTTP 500 Internal Server Error page. | Open
DEF-015 | Cancellation refund amount fails to calculate partial fee deduction | Refund Subsystem | Medium | Medium | 1. Book Advance ticket (£50). 2. Request cancellation within eligible window (subject to £10 fee). | System calculates net refund of £40.00. | System attempts to refund full £50.00 without deducting administration fee. | Ready for Retest